## Dashboard
Delta Crown Owner Decision Workbook
Launch-blocking owner decisions, recommendations, evidence, and follow-up actions
Metric | Value | Why it matters
Workbook purpose | Owner launch decisions | Converts launch blockers into explicit choices.
Decision count | 6 | Six decisions currently block full production-launch claims.
Recommended launch posture | Controlled pilot / owner validation | Built and hardened, but not full production launch yet.
Top technical blocker | Teams channel read context | Members readable; team/channel detail still blocked.
Top governance blocker | Named owners + DLP posture | Needs accountable owners and enforcement decisions.
How to use this workbook
1. Start on Decision Matrix and pick a Tyler decision for each row.
2. Use OD-001 through OD-006 tabs for evidence, risks, options, and recommendation detail.
3. Use Action Tracker to split approved work into small follow-up change issues.
4. Do not make tenant-impacting changes from this workbook alone; create tracked change issues first.

## Decision Matrix
Decision Matrix
One-line view of what Tyler/Megan need to decide
ID | Decision | Current state | Risk | Recommendation | Owner needed | Tyler decision | Decision date | Notes
OD-001 | GitHub default branch / stale main | Remote default branch is main; canonical current project work and GitHub Pages source are on gh-pages. | Future operators may land on stale architecture and treat it as current. | Prefer changing GitHub default branch to gh-pages. If that is not possible, make main a hard redirect/archive branch. | Tyler / repo owner | TBD | TBD
OD-002 | Brand Resources vs Brand Assets model | Docs target Brand Resources; tenant/docs still include Marketing Brand Assets and legacy ClientServices artifacts. | Users and MSP operators may confuse reference material, marketing execution assets, legacy ClientServices, and client records. | Use Brand Resources as the staff-facing reference concept; keep Brand Assets as Marketing execution/library if needed. Do not repurpose ClientServices yet. | Tyler + business/content owner | TBD | TBD
OD-003 | Dynamic security group owners | AllStaff, Managers, Marketing, Stylists, and External have zero owners in Graph. | Nobody is clearly accountable when metadata, membership, or access drifts. | Assign at least two owners per group: MSP/operator plus business/access owner. | Tyler / Megan | TBD | TBD
OD-004 | DLP test mode vs enforce path | DCE-Data-Protection and Corp-Data-Protection are TestWithNotifications; External-Sharing-Block is enabled. | Test mode is not final enforcement. Claims about production DLP must distinguish test from enforce. | Review raw DLP rule details, then choose a staged enforce flip unless rule review proves very low risk. | Tyler + security/compliance owner | TBD | TBD
OD-005 | DeltaCrown-TeamsProvisioner-TEMP app fate | TEMP app registration exists with three password credentials expired on 2026-04-16. | Expired temporary apps are security/governance clutter unless dependency and owner are documented. | Delete the app if no dependency remains. Otherwise rename/document owner and remove expired secrets. | Tyler / tenant app owner | TBD | TBD
OD-006 | ClientServices deprecation banner / cleanup | Legacy ClientServices artifacts are documented as empty/broad and client records are out of M365 scope. | Users may treat old ClientServices resources as approved client-data storage, conflicting with current scope. | Add a visible deprecation/owner note first. Do not delete, rename, or repurpose until owner approval and cleanup plan exist. | Tyler + data/content owner | TBD | TBD

## Action Tracker
Action Tracker
Follow-up actions after decisions are approved
Decision ID | Follow-up action | Type | Owner | Status | Target date | Notes
OD-001 | If A: update GitHub repository default branch setting. | TBD | Tyler / repo owner | Not started | TBD
OD-001 | If B: patch main README to point to gh-pages and warn it is legacy. | TBD | Tyler / repo owner | Not started | TBD
OD-001 | If C: tag legacy main, verify no workflows depend on it, then archive/delete. | TBD | Tyler / repo owner | Not started | TBD
OD-002 | Approve final vocabulary. | TBD | Tyler + business/content owner | Not started | TBD
OD-002 | Create follow-up Brand Resources implementation issue after decision. | TBD | Tyler + business/content owner | Not started | TBD
OD-002 | Do not rename/delete/repurpose live ClientServices resources yet. | TBD | Tyler + business/content owner | Not started | TBD
OD-003 | Name owner candidates for each group. | TBD | Tyler / Megan | Not started | TBD
OD-003 | Create tenant change issue for owner assignment. | TBD | Tyler / Megan | Not started | TBD
OD-003 | Verify owner assignment via Graph after change. | TBD | Tyler / Megan | Not started | TBD
OD-004 | Review local raw DLP rule exports. | TBD | Tyler + security/compliance owner | Not started | TBD
OD-004 | Pick enforce order and maintenance window. | TBD | Tyler + security/compliance owner | Not started | TBD
OD-004 | Create change issue with rollback owner and validation plan. | TBD | Tyler + security/compliance owner | Not started | TBD
OD-005 | Confirm whether any Teams provisioning automation still uses the app. | TBD | Tyler / tenant app owner | Not started | TBD
OD-005 | Create cleanup issue for delete or rename/credential cleanup. | TBD | Tyler / tenant app owner | Not started | TBD
OD-005 | Verify app inventory after cleanup. | TBD | Tyler / tenant app owner | Not started | TBD
OD-006 | Approve banner wording. | TBD | Tyler + data/content owner | Not started | TBD
OD-006 | Create tenant change issue for non-destructive deprecation signal. | TBD | Tyler + data/content owner | Not started | TBD
OD-006 | Decide later: archive, replace, repurpose, or remove. | TBD | Tyler + data/content owner | Not started | TBD

## Evidence
Evidence
Supporting evidence behind recommendations
Decision ID | Evidence | Source / context
OD-001 | git remote show origin reports HEAD branch: main. | See repo docs and owner-decision worksheet.
OD-001 | README says gh-pages is canonical and main is abandoned earlier architecture. | See repo docs and owner-decision worksheet.
OD-001 | Live public site publishes from gh-pages. | See repo docs and owner-decision worksheet.
OD-002 | docs/brand-resources-target-model.md defines Brand Resources as reusable reference material, not CRM/client records. | See repo docs and owner-decision worksheet.
OD-002 | docs/clientservices-to-brand-resources-transition-plan.md says ClientServices assumptions are legacy. | See repo docs and owner-decision worksheet.
OD-002 | docs/legacy-clientservices-cleanup-register.md prohibits tenant cleanup without inventory and approval. | See repo docs and owner-decision worksheet.
OD-003 | docs/delta-crown-identity-inventory-summary.md shows zero owners for all five dynamic groups. | See repo docs and owner-decision worksheet.
OD-003 | Current group counts: AllStaff=6, Managers=1, Marketing=0, Stylists=0, External=0. | See repo docs and owner-decision worksheet.
OD-003 | Production launch readiness report marks named operational owners as a no-go item. | See repo docs and owner-decision worksheet.
OD-004 | docs/delta-crown-compliance-inventory-summary.md lists 6 DLP policies and 8 rules. | See repo docs and owner-decision worksheet.
OD-004 | DCE-Data-Protection mode: TestWithNotifications. | See repo docs and owner-decision worksheet.
OD-004 | Corp-Data-Protection mode: TestWithNotifications. | See repo docs and owner-decision worksheet.
OD-004 | External-Sharing-Block mode: Enable. | See repo docs and owner-decision worksheet.
OD-005 | docs/delta-crown-security-apps-licenses-inventory-summary.md lists DeltaCrown-TeamsProvisioner-TEMP. | See repo docs and owner-decision worksheet.
OD-005 | Inventory found three expired app password credentials for the TEMP app. | See repo docs and owner-decision worksheet.
OD-005 | Safety notes say not to delete app registrations without dependency review and approval. | See repo docs and owner-decision worksheet.
OD-006 | docs/legacy-clientservices-cleanup-register.md states ClientServices/client-record assumptions are legacy. | See repo docs and owner-decision worksheet.
OD-006 | docs/delta-crown-sharepoint-pnp-inventory-summary.md documents ClientServices artifacts and permissions metadata. | See repo docs and owner-decision worksheet.
OD-006 | Brand Resources target model says client records are out of Microsoft 365 scope. | See repo docs and owner-decision worksheet.

## Glossary
Glossary
Plain-English definitions for decision terms
Term | Meaning
DDG | Dynamic Distribution Group for Exchange mail routing.
Dynamic security group | Entra group whose membership is calculated from user attributes.
TestWithNotifications | DLP policy mode that warns/tests without full enforcement.
Brand Resources | Approved staff-facing reference material, not client records.
Brand Assets | Marketing execution/asset library concept.
ClientServices | Legacy concept/artifacts; not approved client-record storage in M365.
Controlled pilot | Limited validation state before full launch approval.

## OD-001
OD-001 — GitHub default branch / stale main
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | Remote default branch is main; canonical current project work and GitHub Pages source are on gh-pages.
Risk | Future operators may land on stale architecture and treat it as current.
Recommendation | Prefer changing GitHub default branch to gh-pages. If that is not possible, make main a hard redirect/archive branch.
Owner needed | Tyler / repo owner
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Change GitHub default branch to gh-pages. | Repo landing page matches current work. | Requires GitHub repo admin action.
B | Keep main but replace README with a clear redirect to gh-pages. | Fast and low risk. | Users can still browse stale files.
C | Archive/delete stale main after preservation tag. | Cleanest long-term. | Higher governance risk; needs explicit approval.
Supporting evidence
Evidence | Detail
Evidence | git remote show origin reports HEAD branch: main.
Evidence | README says gh-pages is canonical and main is abandoned earlier architecture.
Evidence | Live public site publishes from gh-pages.
Follow-up actions
Action | Detail
Action | If A: update GitHub repository default branch setting.
Action | If B: patch main README to point to gh-pages and warn it is legacy.
Action | If C: tag legacy main, verify no workflows depend on it, then archive/delete.

## OD-002
OD-002 — Brand Resources vs Brand Assets model
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | Docs target Brand Resources; tenant/docs still include Marketing Brand Assets and legacy ClientServices artifacts.
Risk | Users and MSP operators may confuse reference material, marketing execution assets, legacy ClientServices, and client records.
Recommendation | Use Brand Resources as the staff-facing reference concept; keep Brand Assets as Marketing execution/library if needed. Do not repurpose ClientServices yet.
Owner needed | Tyler + business/content owner
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Brand Resources = staff reference; Brand Assets = Marketing execution library. | Clear separation of audience and purpose. | Requires explaining two related terms.
B | Consolidate everything to Brand Resources. | Simplest user-facing label. | Unsafe before dependency/content review.
C | Keep Brand Assets as the only user-facing term. | Matches current Marketing wording. | Weakens replacement of ClientServices assumptions.
D | Defer until owners classify current usage. | Avoids premature naming decision. | Slows launch cleanup.
Supporting evidence
Evidence | Detail
Evidence | docs/brand-resources-target-model.md defines Brand Resources as reusable reference material, not CRM/client records.
Evidence | docs/clientservices-to-brand-resources-transition-plan.md says ClientServices assumptions are legacy.
Evidence | docs/legacy-clientservices-cleanup-register.md prohibits tenant cleanup without inventory and approval.
Follow-up actions
Action | Detail
Action | Approve final vocabulary.
Action | Create follow-up Brand Resources implementation issue after decision.
Action | Do not rename/delete/repurpose live ClientServices resources yet.

## OD-003
OD-003 — Dynamic security group owners
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | AllStaff, Managers, Marketing, Stylists, and External have zero owners in Graph.
Risk | Nobody is clearly accountable when metadata, membership, or access drifts.
Recommendation | Assign at least two owners per group: MSP/operator plus business/access owner.
Owner needed | Tyler / Megan
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Two owners per group: MSP operator + business/access owner. | Best production governance. | Requires naming humans now.
B | One central identity owner for all dynamic groups. | Fastest owner assignment. | Weak business accountability.
C | Keep ownerless until metadata cleanup finishes. | Avoids churn. | Leaves governance gap open.
Supporting evidence
Evidence | Detail
Evidence | docs/delta-crown-identity-inventory-summary.md shows zero owners for all five dynamic groups.
Evidence | Current group counts: AllStaff=6, Managers=1, Marketing=0, Stylists=0, External=0.
Evidence | Production launch readiness report marks named operational owners as a no-go item.
Follow-up actions
Action | Detail
Action | Name owner candidates for each group.
Action | Create tenant change issue for owner assignment.
Action | Verify owner assignment via Graph after change.

## OD-004
OD-004 — DLP test mode vs enforce path
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | DCE-Data-Protection and Corp-Data-Protection are TestWithNotifications; External-Sharing-Block is enabled.
Risk | Test mode is not final enforcement. Claims about production DLP must distinguish test from enforce.
Recommendation | Review raw DLP rule details, then choose a staged enforce flip unless rule review proves very low risk.
Owner needed | Tyler + security/compliance owner
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Keep test mode for 30 days and review alerts. | Lower business disruption risk. | Not fully enforcing.
B | Flip both policies to enforce in one window. | Fastest enforcement posture. | Higher false-positive risk.
C | Enforce one policy first, then the other. | Balanced staged rollout. | Takes longer.
D | Keep test mode indefinitely. | Avoids disruption. | Not production-grade.
Supporting evidence
Evidence | Detail
Evidence | docs/delta-crown-compliance-inventory-summary.md lists 6 DLP policies and 8 rules.
Evidence | DCE-Data-Protection mode: TestWithNotifications.
Evidence | Corp-Data-Protection mode: TestWithNotifications.
Evidence | External-Sharing-Block mode: Enable.
Follow-up actions
Action | Detail
Action | Review local raw DLP rule exports.
Action | Pick enforce order and maintenance window.
Action | Create change issue with rollback owner and validation plan.

## OD-005
OD-005 — DeltaCrown-TeamsProvisioner-TEMP app fate
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | TEMP app registration exists with three password credentials expired on 2026-04-16.
Risk | Expired temporary apps are security/governance clutter unless dependency and owner are documented.
Recommendation | Delete the app if no dependency remains. Otherwise rename/document owner and remove expired secrets.
Owner needed | Tyler / tenant app owner
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Delete app after dependency check. | Cleanest if no longer used. | Requires confidence no automation depends on it.
B | Keep, rename, assign owner, remove expired credentials, document purpose. | Safe if still needed. | Keeps extra app surface.
C | Keep as-is temporarily with deadline. | Buys time. | Still leaves known smell.
Supporting evidence
Evidence | Detail
Evidence | docs/delta-crown-security-apps-licenses-inventory-summary.md lists DeltaCrown-TeamsProvisioner-TEMP.
Evidence | Inventory found three expired app password credentials for the TEMP app.
Evidence | Safety notes say not to delete app registrations without dependency review and approval.
Follow-up actions
Action | Detail
Action | Confirm whether any Teams provisioning automation still uses the app.
Action | Create cleanup issue for delete or rename/credential cleanup.
Action | Verify app inventory after cleanup.

## OD-006
OD-006 — ClientServices deprecation banner / cleanup
Decision detail, options, evidence, and action prompts
Field | Detail
Current state | Legacy ClientServices artifacts are documented as empty/broad and client records are out of M365 scope.
Risk | Users may treat old ClientServices resources as approved client-data storage, conflicting with current scope.
Recommendation | Add a visible deprecation/owner note first. Do not delete, rename, or repurpose until owner approval and cleanup plan exist.
Owner needed | Tyler + data/content owner
Tyler selected option | TBD
Approval / date | TBD
Follow-up issue | TBD
Options
Option | Description | Pros | Cons
A | Add deprecation/banner notice: do not use for client records; pending cleanup. | Immediate clear signal without destructive changes. | Requires tenant page/banner edit.
B | Remove navigation links only. | Reduces accidental use. | Does not explain what happened.
C | Archive or delete after owner approval. | Cleaner long-term. | Unsafe before dependency/content approval.
D | Repurpose as Brand Resources after approval. | May reuse existing resource. | Risky URL/history/permission baggage.
Supporting evidence
Evidence | Detail
Evidence | docs/legacy-clientservices-cleanup-register.md states ClientServices/client-record assumptions are legacy.
Evidence | docs/delta-crown-sharepoint-pnp-inventory-summary.md documents ClientServices artifacts and permissions metadata.
Evidence | Brand Resources target model says client records are out of Microsoft 365 scope.
Follow-up actions
Action | Detail
Action | Approve banner wording.
Action | Create tenant change issue for non-destructive deprecation signal.
Action | Decide later: archive, replace, repurpose, or remove.